## Agile Project Plan - Example
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
| Product Release | Alex B. | 2019-09-02 | 2019-10-10 |  | 20% |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Sprint 1 |  | Alex B. |  | 2019-09-03 | 2019-09-13 | 10 | Complete
| Feature 1 |  | Frank C. |  | 2019-09-03 | 2019-09-07 | 4 | Complete
| Feature 2 |  | Jacob S. |  | 2019-09-07 | 2019-09-12 | 5 | Complete
| Feature 3 |  | Jacob S. |  | 2019-09-09 | 2019-09-13 | 4 | Overdue
| Sprint 2 |  | Jacob S. |  | 2019-09-16 | 2019-09-24 | 8 | In Progress
| Feature 4 |  | Alex B. |  | 2019-09-16 | 2019-09-17 | 1 | In Progress
| Feature 5 |  | Frank C. |  | 2019-09-17 | 2019-09-21 | 4 | Not Started
| Feature 6 |  | Shari W. |  | 2019-09-22 | 2019-09-24 | 2 | Not Started
| Sprint 3 |  | Shari W. |  | 2019-09-25 | 2019-10-05 | 10 | Not Started
| Feature 7 |  | Alex B. |  | 2019-09-25 | 2019-09-29 | 4 | Not Started
| Feature 8 |  | Kennedy K. |  | 2019-09-24 | 2019-10-02 | 8 | Not Started
| Feature 9 |  | Jacob S. |  | 2019-10-02 | 2019-10-05 | 3 | Not Started

## Agile Project Plan
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
| Movie Database | Sprint 1: Kyer Potts Sprint 2: Luke Gough Sprint 3: Brandon Price | 2019-11-05 | 2019-11-17 |  |  |  | SCOPE STATEMENT
Completed | TASK NAME |  | RESPONSIBLE | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Sprint 1 |  | Kyer Potts | 2019-11-05 | 2019-11-12 | 7 | Completed
| Set up Source Control |  | Luke Gough | 2019-11-05 | 2019-11-05 | 1 | Completed | GitHub account set up with repositories.
| Setup Project Plan |  | Kyer Potts | 2019-11-05 | 2019-11-05 | 1 | Completed | Agile Project Plan created and uploaded to GitHub.
| Setup Front End |  | Luke Gough | 2019-11-06 | 2019-11-07 | 2 | Completed | Front end has been setup, configured and uploaded to GitHub.
| Setup Back End |  | Luke Gough | 2019-11-06 | 2019-11-07 | 2 | Completed | Back end has been setup, configured and uploaded to GitHub.
| Software Development Master Document |  | Kyer Potts | 2019-11-05 | 2019-11-12 | 7 | Completed | Document setup and formatted to accept all sub documents.
| Software Testing Plan |  | Brandon Price | 2019-11-07 | 2019-11-11 | 4 | Completed | Software Testing Plan is pending completion form Brandon Price.
| Software Analysis Report |  | Kyer Potts | 2019-11-05 | 2019-11-12 | 7 | Completed | Document setup and added to Master Document.
| Multi-Platform Report(Adaptive v Responsive) |  | Kyer Potts | 2019-11-05 | 2019-11-12 | 7 | Completed | Document setup and added to Master Document.
| Demonstration Movie Database App |  | Kyer Potts | 2019-11-12 | 2019-11-12 | 1 | Completed | Sprint 1 demonstation has been prestened to the client.
Sprint 2
| Source Control Snapshot |  | Luke Gough | 2019-11-19 | 2019-11-19 | 7 | TBC | TBC once all code and documentation has been uploaded.
| Software Review Plan |  | Luke Gough | 2019-11-12 | 2019-11-18 | 6 | TBC | TBC
| Performance Report |  | Luke Gough | 2019-11-12 | 2019-11-18 | 6 | TBC | TBC
| Update Project Management Plan |  | Luke Gough | 2019-11-12 | 2019-11-13 | 1 | Completed | Project Management Plan has been updated.
| Update Software Testing Plan |  | Luke Gough | 2019-11-12 | 2019-11-18 | 6 | TBC | TBC
| Membership Subscription Page |  | Kyer Potts | 2019-11-12 | 2019-11-16 | 4 | TBC | TBC
| Administrator Subscriber removal Page |  | Kyer Potts | 2019-11-12 | 2019-11-16 | 4 | TBC | TBC
| Software Testing Plan |  | Brandon Price | 2019-11-16 | 2019-11-18 | 2 | TBC | TBC
Sprint 3
Feature 4
Feature 4
Feature 4